## jira_example
Issue key | Summary | Description | Assignee | Created | Updated | Resolved
AFM-3224 | Can't close sidebar in some situations | When left navigation panel is open OR smaller screen sizes. This is a bug in the currently used version of the side panel of the design system | Alan Lawrence | 2021-02-04 10:19 | 2021-02-15 17:46 | 2021-02-11 15:54
AFM-3185 | Change text on login page | theme/login.html PO: From â€œKeep Our Data Privateâ€Â Toâ€œ *Check Our Data Privacy*â€, the text underneath that is fine as it is. The text in the microsoft button to use for SSO â†’ check what text we show in other apps and change to that text | Beatrice Peters | 2021-01-29 12:13 | 2021-02-11 15:58 | 2021-02-10 12:43
AFM-3184 | Change a number of text and positioning in wizard layout (and home page) | * in step 2 place profiling at the bottom of the form (under data categories) * default setting of the 'method of notification checkbox' (boolean) should be off not on * in step 1 the text on the chechbox for 'third party' needs to be changed ( from party --> by party) * placeholder text of the legitimate interest comment box needs to be changed â†’ â€œ_Please motivate your legitimate interest and what impact it has on the privacy of the individual and what measures you take to limit this privacy impactâ€_ * placeholder text of method of notification --> instead of how did you notifiy, how do you notifiy (confirm with PO) * -background colour homepages (user, process owner, privacy manager) should be white not grey. Take off bg-secondary class on the pages- had already been done * -change header of list view to 'Processing activities of my department' on home_processowner- had already been done * remove administrator settings pages and add those to the navigation menu for privacy managers only | Camelia Brown | 2021-01-29 12:12 | 2021-02-11 11:10 | 2021-02-10 12:58
AFM-3183 | Give confirmation on submit buttons in wizard | * Give a confirmation pop-up that asks you: Are you sure you want to submit your processing activity? A privacy manger will either approve or reject your submission. If you havenâ€™t finished yet you can save your processing activity as a draft at the top of the page and submit at a later point in time. | Beatrice Peters | 2021-01-29 12:06 | 2021-02-12 11:04 | 2021-02-08 16:22
AFM-3182 | Change a number of styling issues from usability test | * FAQ yellow colour box (to be updated by Anne) * reposition of FAQ send a request to privacy manager + add a faq (check with Anne) * hover on list on FAQ, turn it off (thereâ€™s existing class for that) EDIT: If time allows, this was not originally estimated but here as a reminder. *If time does not allow these additional comments from PO checks create a task for this on the backlog*\! * Header large on home pages if not searching â†’ almost half page see Anne design * make spacing about page, reports, recent update on the left equal to the detail pages (margin-left of the header should be the same) !image-20210210-142952.png¦width=1289,height=815! | Beatrice Peters | 2021-01-29 12:05 | 2021-02-12 11:29 | 2021-02-11 14:55
AFM-3159 | Update Notification dropdown | First version of design: !image-2021-01-21-10-25-10-943.png¦width=200,height=183! To Do: * Add a bullet to the right side to mark the notification as read/unread. This is a replacement of the text 'Mark as read'. * Show a maximum of 4 notifications in the dropdown menu. * Add a 'See more' button at the bottom of the list to load more notifications. Use the scrollbar to go through the list. * Delete the 'delete' function in the dropdown. * Scheduled event - edit the existing one that deletes all messages, make sure to only deleted read messages that have existed half a year Food for thoughts for later: What to do if the list of notifications becomes too long? -> separate page with all notifications, or delete notification after a certain time. | Daisy Rogers | 2021-01-21 10:25 | 2021-02-11 11:53 | 2021-02-11 09:45
AFM-3112 | Add 'Recent updates' section to the pages | Add the Recent Updates to the following page: * Homepage, including result page after searching. Design can be found here: [https://paper.dropbox.com/doc/Recent-Updates--BDvtIEQ7Xkv6FFIo6xwvVfybAg-j1epgdImdfllMdncn9lZ7¦https://paper.dropbox.com/doc/Recent-Updates--BDvtIEQ7Xkv6FFIo6xwvVfybAg-j1epgdImdfllMdncn9lZ7] The shown content depends on the type of user: Privacy Manager: * Status updates (submit/approved/rejected) of activities * The last added FAQâ€™s (multiple possible) * added objects Process owner: * Status updates (submit/approved/rejected) of activities of *their department.* * The last added FAQâ€™s (multiple possible) * added objects Users: * Status updates of approved activities (or if they have chosen a relevant department, then only from department) * The last added FAQâ€™s (multiple possible) Question to POâ€™s: how often is an object edited? Interesting to show the change to the process owner? Answer: No often done â†’ dont show in recent updates. For the users, if they have selected a department, do they still see Status updates of activities from all or only their own deparment? â†’ only their department | Edwin Harrison | 2021-01-12 10:53 | 2021-02-11 18:36 | 2021-02-11 14:08
AFM-3019 | As a user I want to learn more about the type of information shown on the Detail pages | To make it clear for the users what the displayed information (e.g. data subjects) means on the detail page, an explanation is needed. This could be something similar as the marketing boxes used in the process activity form. Edit: All information boxes we show in the wizard that are applicable to the information on the detail page should have a tooltip | Edwin Harrison | 2020-12-15 14:34 | 2021-01-27 17:56 | 2021-01-27 15:41
AFM-2847 | As a privacy manager I want to be able to assign a user to a department to make them a process owner |  | Camelia Brown | 2020-11-20 13:24 | 2020-12-04 10:43 | 2020-11-30 09:52
AFM-2967 | Improve step 2 and 3 of the wizard | * The list views in step 2 are still shown when empty. * [https://paper.dropbox.com/doc/Wizard-step-2-3-sidepanels--BBRl3s_sMHkPxmYyFSo3YYgfAg-79nlqo3Y9pG7McNm1pJfm¦https://paper.dropbox.com/doc/Wizard-step-2-3-sidepanels--BBRl3s_sMHkPxmYyFSo3YYgfAg-79nlqo3Y9pG7McNm1pJfm] *Make sure to check dropbox for latest version design before starting story\!* Make sure the logic of validation, adding new and such are taken into account now that everything is going to be in the form itself | Daisy Rogers | 2020-12-03 10:28 | 2021-01-07 15:46 | 2021-01-07 12:03
AFM-2966 | Add side panels in the wizard | * Every add card (button) in the wizard must show a side panel. * [https://docs.mendix.com/howto/front-end/use-navigation-layouts#1-introduction¦https://docs.mendix.com/howto/front-end/use-navigation-layouts#1-introduction] * Advice: use a pop-up page, change the opacity (so that whatâ€™s behind doesnâ€™t become darker like a pop-up, make the width about half of the screen * [https://paper.dropbox.com/doc/Wizard-step-2-3-sidepanels--BBRl3s_sMHkPxmYyFSo3YYgfAg-79nlqo3Y9pG7McNm1pJfm¦https://paper.dropbox.com/doc/Wizard-step-2-3-sidepanels--BBRl3s_sMHkPxmYyFSo3YYgfAg-79nlqo3Y9pG7McNm1pJfm] *Make sure to check dropbox for latest version design before starting story\!* {panel:bgColor=#deebff} * *PO feedback on the about page being the only page in the application with an url:* unnecessary, urls to bookmark are not needed at the moment. This can be removed. {panel} | Camelia Brown | 2020-12-03 10:25 | 2021-01-07 15:46 | 2021-01-07 12:03
AFM-3030 | Instead of having the information boxes always open, I want to click an 'i' icon and have only one box open at a time | # the user should see an i icon next to information in the wizard forms (step 1 to 4) that can show an â€˜information boxâ€™ # the user should click on the icon to open the box # when the user clicks on another icon the already open box should close when the new box is opened to ensure the user does not get overwhelmed and thereâ€™s never a risk of boxes overlapping # when entering a wizard page the first information box should be open ideally | Camelia Brown | 2020-12-17 15:10 | 2021-01-13 16:28 | 2021-01-13 14:46
AFM-2856 | As a process owner, I want to create a draft (so i can edit before submitting) and submit my processing activity | {panel:bgColor=#deebff} *Question: is a process owner able to submit an imcomplete processing activity?* *Answer Simone*: yes for the following reason: I would rather have that a process owner records something for which he/she cannot fulfill all information than become frustrated because he/she does not know all information and then leave it there. Entering an activity should give as little effort as possible because it is not seen as a fun task for the process owner. So rather an incomplete entry than none. The process owner should be able to navigate between steps. Save behaviour should be on all next and previous step buttons. {panel} | Edwin Harrison | 2020-11-20 13:53 | 2021-01-06 10:01 | 2021-01-05 15:45
AFM-2792 | As a user I want to be able to view the detail page of a processing activity | Check if thereâ€™s an existing detail page Show detail pages once they click on an activity on the overview page # Should have edit button on detail page * processing activity details does not need associations tab as all that information is visible on the overview * association details are meant for looking at data subjects and these kind of pages Search should be restricted by xpath first based on associations [https://paper.dropbox.com/doc/Design-DPR--BDRgEYmSBcvfxaEfHpCzTx1FAg-zsMaz0XMF8Uhk66NeumGW¦https://paper.dropbox.com/doc/Design-DPR--BDRgEYmSBcvfxaEfHpCzTx1FAg-zsMaz0XMF8Uhk66NeumGW] | Camelia Brown | 2020-11-18 11:26 | 2021-01-22 16:44 | 2021-01-22 12:18
AFM-2516 | As Privacy Manager, I want to be able to add and change FAQ's, so I can answer all FAQ's about the processing activities and the register in general | * FAQ page (connected to the about page) * Clear overview of questions (toggle down for the answers) * FAQ should have a category thatâ€™s configurable, (standard admin page where these can be maintained is fine) See design of the page in dropbox + questions/remarks from Anne about the design: # you can scroll down or load more for more results # if the text is long donâ€™t show the entire text immediately but click on it to view more. # There should be an FAQ button on the about page In addition, POâ€™s mentioned that maybe searching via tag or categories would help. | Edwin Harrison | 2020-09-30 09:24 | 2021-01-25 14:18 | 2021-01-22 13:40
AFM-2518 | As a Privacy Manager, I want to create reports of my searches, so I can share it with external parties if they ask for. | * Export to excel button Only approved activities need to be included in the report. Only showing the name of the processing activity in the report as a column is sufficient. List of filters: *Processing activity itself:* # Data collected by third party Y/N # Notified data collection Y/N # Profiling Y/N # Joint data controller applicable Y/N *Region:* Filter with regions, you select a region to filter *Department:* List with departments, you select a department to filter on Â *Security Measures:* list with security measures, you select a security measure to filter onÂ *Data controller:* List with data controllers, you select a datacontroller to filter on List with joint data controllers, you select a data controller to filter on *Data subject:* List with data subjects, you select a data subject to filter on *Data category:* List with data categories, you select a data category to filter on Sensitive Data Y/N as seperate filter. When you put this on yes youâ€™ll get all processing activities wherein a datacategory with sensitive data is chosenÂ *Legal Bases:* List with legal bases, you select a legal basis to filter on *Processor:* List with Processors, you select a processor to filter on Processor in EU Y/N as seperate filter, IF you put this one on yes you get all processing activities whering a processor is used thatâ€™s located in the EU. Processor Agreement Available Y/N als apart filter, if you put this on yes you get processing activities whering a processor is used for which a processing agreement is available.Â *Safeguards:* List with safeguards, when you select one, you get a list of processing activities wherin a processor is used with this safeguard. | Fabian Davison | 2020-09-30 09:24 | 2021-02-05 13:52 | 2021-02-04 14:59
AFM-2522 | As a Privacy Manager I want to have a comment box for the legal basis " Legitimate interest" so I can provide information about legitimate interest which is a legal obligation | * comment box {panel:bgColor=#deebff} *Question: The comment box is only for this legal basis in the wizard step 4?* Answer PO: Legitimate interest is one of the six legal basis options, the comment box is *only for this option* *Question: Where to place the comment box* Conclusion: Underneath the rest of the fields in the form as a wide box {panel} | Gloria Blanton | 2020-09-30 09:24 | 2020-12-14 09:48 | 2020-12-10 12:00
AFM-2631 | Implement wizard design for the process activity flow | * the current application has an existing wizard, but not in the desired style of the design. This should be updated, see file * [https://paper.dropbox.com/doc/Design-DPR--BAOwqXVceiTvZFDZSnLTsQQQAg-zsMaz0XMF8Uhk66NeumGW¦https://paper.dropbox.com/doc/Design-DPR--BAOwqXVceiTvZFDZSnLTsQQQAg-zsMaz0XMF8Uhk66NeumGW] {panel:bgColor=#deebff} *Info for peer review: please only review the design* *See the new design in the attachments.* * Review page is not necessary. * Status badge will be implemented in a story in the backlog. * Info underneath the steps is not necessary. * The list views in *step 2* are still shown even when empty. This will be fixed once merged with dev line, as that line has the layout helper entity. * *Step 3* is still in progress. Not sure if the card add button will be used or just use regular buttons shown. Anne will let us know today. *Please keep this in mind when peer reviewing.* {panel} | Alan Lawrence | 2020-10-13 14:21 | 2020-12-07 13:13 | 2020-12-02 12:45
AFM-2505 | As a Process Owner, I want to know which status a processing activity has | There are 4 statuses * *Draft* (process owner has recorded the processing activity in the app but did not submit the activity, so (s)he can edit it) * *Submitted* (the process owner submitted the processing activity, so the privacy manager can review it) * *Approved* (the privacy manager reviews the processing activity and can adjust the activity and approves the activity. The processing activity is visible for all now) * *Rejected* (the privacy manager rejects the processing activity, the process owner will get feedback by email why the processing activity is rejected, the processing activity will not be visible for all). | Camelia Brown | 2020-09-30 09:24 | 2021-01-14 11:27 | 2021-01-14 09:55